## About
ABOUT THIS GANTT CHART
Visualise and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Green
UoN Browser Based Collaborative Workspace
Company name
Project lead
Project start date: | 2023-11-06 | [10 empty] | Scrolling increment: | [5 empty] | 0
Milestone marker: | 1 | 1 |  |  | November | [27 empty] | December | [27 empty] | January | [30 empty] | February | [28 empty] | March | [30 empty] | April | [29 empty] | May
 | time axis 2023-11-06 to 2024-05-31
Milestone description | Assigned to | Progress | Start | Days | time axis 2023-11-06 to 2024-05-31
Documentation
Documentation | Everyone | 25% | 2023-11-06 | 9
Interim Report | Manasi | 33% | 2023-11-06 | 40 | 2023-12-20: Christmas Holidays; 2024-03-05: Easter Holidays
Final Report | Everyone | 50% | 2023-11-06 | 183
Peer Review | Everyone |  | 2024-02-21 | 1 | bar: 2024-02-21
Demonstration | Everyone |  | 2024-04-30 | 17
Individual Reports | Everyone | 10% | 2023-11-06 | 40
Research
Similar Apps | Everyone | 60% | 2023-11-13 | 9
Exisiting Libraries | Everyone | 50% | 2023-11-13 | 15
Research Write-up | Everyone | 33% | 2023-11-13 | 15
Server Management Research | Back-end |  | 2023-11-13 | 20
Market Research + Survey | Indy and Ian |  | 2023-11-13 | 9
App Planning
Requirement Gathering | Manasi |  | 2023-11-06 | 9
Use Cases | Varsh |  | 2023-11-06 | 9
Activity Diagram | Amal |  | 2023-11-06 | 9
Sequence Diagram | Sam and Jackson |  | 2023-11-06 | 9
Personas and User Stories | Megan and Nicole |  | 2023-11-06 | 9
Prototype | Megan and Sam |  | 2023-11-13 | 9
Testing
Black box |  |  | 2024-03-09 | 15
Unit Tests |  |  | 2024-01-16 | 65
Integration Test |  |  | 2024-01-23 | 30
Acceptance Tests |  |  | 2024-01-25 | 15
User Feedback |  |  | 2024-01-25 | 85
Implementation
GUI | Front-end |  | 2023-12-04 | 160 | bar: 2023-11-14 to 2023-12-13; 2024-01-10 to 2024-05-05
Server Management | Back-end |  | 2023-12-11 | 146 | bar: 2023-12-12 to 2023-12-13; 2024-01-10 to 2024-05-05
Database Mangement | Back-end
Uploading photos | Back-end
To add more data, Insert new rows ABOVE this one

## Blue
Project title
Company name
Project lead
Project start date: | 2024-01-29 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | February | [20 empty] | March
 | time axis 2024-02-11 to 2024-04-06
Milestone description | Assigned to | Progress | Start | Days | time axis 2024-02-11 to 2024-04-06
Title 1
Task 1 |  | 25% | 2024-02-01 | 3
Task 2 |  |  | 2024-02-06 | 1
Task 3 |  | 50% | 2024-01-29 | 10
Task 4 |  |  | 2024-02-21 | 1 | bar: 2024-02-21
Task 5 |  | 10% | 2024-02-07 | 6
Title 2
Task 1 |  | 60% | 2024-02-07 | 13
Task 2 |  | 50% | 2024-02-08 | 9
Task 3 |  | 33% | 2024-02-16 | 11
Task 4 |  |  | 2024-02-25 | 1 | bar: 2024-02-25
Task 5 |  |  | 2024-02-26 | 24
Title 3
Task 1 |  |  | 2024-02-16 | 4
Task 2 |  |  | 2024-02-20 | 14
Task 3 |  |  | 2024-03-07 | 6
Task 4 |  |  | 2024-03-20 | 3
Task 5 |  |  | 2024-03-12 | 19
Title 4
Task 1 |  |  | 2024-03-09 | 15
Task 2 |  |  | 2024-03-01 | 5
Task 3 |  |  | 2024-04-21 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Purple
Project title
Company name
Project lead
Project start date: | 2024-01-29 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | February | [20 empty] | March
 | time axis 2024-02-11 to 2024-04-06
Milestone description | Assigned to | Progress | Start | Days | time axis 2024-02-11 to 2024-04-06
Title 1
Task 1 |  | 25% | 2024-02-01 | 3
Task 2 |  |  | 2024-02-06 | 1
Task 3 |  | 50% | 2024-01-29 | 10
Task 4 |  |  | 2024-02-21 | 1 | bar: 2024-02-21
Task 5 |  | 10% | 2024-02-07 | 6
Title 2
Task 1 |  | 60% | 2024-02-07 | 13
Task 2 |  | 50% | 2024-02-08 | 9
Task 3 |  | 33% | 2024-02-16 | 11
Task 4 |  |  | 2024-02-25 | 1 | bar: 2024-02-25
Task 5 |  |  | 2024-02-26 | 24
Title 3
Task 1 |  |  | 2024-02-16 | 4
Task 2 |  |  | 2024-02-20 | 14
Task 3 |  |  | 2024-03-07 | 6
Task 4 |  |  | 2024-03-20 | 3
Task 5 |  |  | 2024-03-12 | 19
Title 4
Task 1 |  |  | 2024-03-09 | 15
Task 2 |  |  | 2024-03-01 | 5
Task 3 |  |  | 2024-04-21 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one